## Blank Sheet
Project Estimating & ROI Approval
Cost/Benefit Category |  | Personnel | Purchased | Other | Total | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10
Project Costs
| Category 1 |  |  |  | 0
| Category 2 |  |  |  | 0
| Category 3 |  |  |  | 0
| Category 4 |  |  |  | 0
| Category 5 |  |  |  | 0
| Category 6 |  |  |  | 0
| Category 7 |  |  |  | 0
| Category 8 |  |  |  | 0
Total Project Costs |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Operating Expenses - Cost & Benefit
| Addition of New Operating Expenses |  |  |  | 0
| Elimination of Old Operating Expenses |  |  |  | 0
Total Operating Expenses |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sales Impact - Cost & Benefit
| New Sales |  |  |  | 0
| Variable Cost of New Sales |  |  |  | 0
| Sales Loss (negative number) |  |  |  | 0
| Variable Cost of Sales Loss (positive number) |  |  |  | 0
Total Sales Impact |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Period total | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cumulative total | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Call Center Project
Project Estimating & ROI Approval |  |  |  | Call Center Upgrade Project
Cost/Benefit Category |  |  | Personnel | Purchased | Other | Total | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8
Project Costs
| Project Management |  |  |  |  | 0
|  | Project manager for 14 months | -56000 |  |  | -56000 | Year 1: -48000; Year 2: -8000
|  | Travel expenses for supplier visits |  |  | -15000 | -15000 | Year 1: -15000
| Call Center |  |  |  |  | 0
|  | Project support one person 14 months | -84000 |  |  | -84000 | Year 1: -72000; Year 2: -12000
|  | User Testing 3 people for 2 months | -30000 |  |  | -30000 | Year 2: -30000
|  | Training of 70 people | -84000 |  |  | -84000 | Year 2: -84000
| IT |  |  |  |  | 0
|  | Requirements definitino | -15000 |  |  | -15000 | Year 1: -15000
|  | System Architecture | -75000 |  |  | -75000 | Year 1: -75000
|  | Unit testing & supplier support | -110000 |  |  | -110000 | Year 1: -110000
|  | System and user testing | -155000 |  |  | -155000 | Year 2: -155000
|  | Hardware Installation | -80000 |  |  | -80000 | Year 1: -80000
|  | Documentation | -140000 |  |  | -140000 | Year 1: -70000; Year 2: -70000
| Purchasing |  |  |  |  | 0
|  | System software suppplier |  | -1200000 |  | -1200000 | Year 1: -1200000
|  | Hardware |  | -70000 |  | -70000 | Year 1: -70000
|  | Oversight and support at #1,200 per mo. | -16800 |  |  | -16800 | Year 1: -14400; Year 2: -2400
Total Project Costs |  |  | -845800 | -1270000 | -15000 | -2130800 | -1769400 | -361400 | 0 | 0 | 0 | 0 | 0 | 0
Operating Expenses - Cost & Benefit
| Call Center |  |  |  |  | 0
|  | Productivity from reduced errors | 330000 |  |  | 330000 |  | 275000 | 330000 | 330000 | 330000 | 330000 | 330000 | 330000
| IT |  |  |  |  | 0
|  | Maintenance |  |  | 96000 | 96000 |  | 80000 | 96000 | 96000 | 96000 | 96000 | 96000 | 96000
Total Operating Expenses |  |  | 330000 | 0 | 96000 | 426000 | 0 | 355000 | 426000 | 426000 | 426000 | 426000 | 426000 | 426000
Sales Impact - Cost & Benefit
| New Sales |  | $1,500,000 per year - growing $100,000 |  |  | 0 |  | 1250000 | 1600000 | 1700000 | 1800000 | 1900000 | 2000000 | 2100000
| Variable Cost of New Sales |  | -$900,000 per year - growing -$60,000 |  |  | 0 |  | -750000 | -960000 | -1020000 | -1080000 | -1140000 | -1200000 | -1260000
| Sales Loss (negative number) |  | none |  |  | 0
| Variable Cost of Sales Loss (positive number) |  |  |  |  | 0
Total Sales Impact |  |  | 0 | 0 | 0 | 0 | 0 | 500000 | 640000 | 680000 | 720000 | 760000 | 800000 | 840000
Period total | [6 empty] | -1769400 | 493600 | 1066000 | 1106000 | 1146000 | 1186000 | 1226000 | 1266000
Cumulative total | [6 empty] | -1769400 | -1275800 | -209800 | 896200 | 2042200 | 3228200 | 4454200 | 5720200
|  | This project has the highest NPV |  | ` | 12% | NPV | Year 1: 2330753.6366

## NPD Project
Project Estimating & ROI Approval |  |  | Product Development Project
Cost/Benefit Category |  | Personnel | Purchased | Other | Total | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8
Project Costs
| Hardware Development | -50000 | -20000 |  | -70000 | Year 1: -70000
| Software Development | -95000 |  |  | -95000 | Year 1: -95000
| Prototypes | -20000 | -35000 | -15000 | -70000 | Year 1: -70000
| Development Testing | -65000 |  |  | -65000 | Year 1: -65000
| Qualification Testing | -57000 |  | -23000 | -80000 | Year 1: -40000; Year 2: -40000
| Tooling & Test Equipment | -30000 | -60000 | -5000 | -95000 | Year 1: -95000
| Manufacturing Pilot Run | -14000 | -19000 |  | -33000 | Year 2: -33000
| System Upgrades | -31000 |  |  | -31000 | Year 1: -20000; Year 2: -11000
| Advertising Campaign | -20000 | -45000 | -12000 | -77000 | Year 1: -53000; Year 2: -24000
| Market Launch | -15000 | -15000 | -15000 | -45000 | Year 2: -45000
Total Project Costs |  | -397000 | -194000 | -70000 | -661000 | -508000 | -153000 | 0 | 0 | 0 | 0 | 0 | 0
Operating Expenses - Cost & Benefit
| Increased annual advertising |  | -50000 |  | -50000 |  |  | -50000 | -50000 | -50000 | -50000 | -50000 | -50000
Total Operating Expenses |  | 0 | -50000 | 0 | -50000 | 0 | 0 | -50000 | -50000 | -50000 | -50000 | -50000 | -50000
Sales Impact - Cost & Benefit |  |  |  | Project Sales Volumne |  |  | 5000 | 12000 | 12000 | 10000 | 9000 | 8100 | 7290
| Price - online retail (70% of sales) |  |  | 149.9 |  |  | 524650 | 1259160 | 1259160 | 1049300 | 944370 | 849933 | 764939.7
| Price - wholesale (30% of sales |  |  | 107.5 |  |  | 161250 | 387000 | 387000 | 322500 | 290250 | 261225 | 235102.5
| COGS per unit | -26.55 | -47.3 | -7.45 | -81.3 |  | -406500 | -975600 | -975600 | -813000 | -731700 | -658530 | -592677
Total Sales Impact | [5 empty] | 0 | 279400 | 670560 | 670560 | 558800 | 502920 | 452628 | 407365.2
Period total | [5 empty] | -508000 | 126400 | 620560 | 620560 | 508800 | 452920 | 402628 | 357365.2
Cumulative total | [5 empty] | -508000 | -381600 | 238960 | 859520 | 1368320 | 1821240 | 2223868 | 2581233.2
|  |  | Discount Rate | 12% | NPV | Year 1: 1325600.5709