## Planner Tasks
Employee Onboarding Plan
Task number | Name | Duration | Start | Due Date | % complete | Bucket | Labels | Priority
1 | Set employee start date in system | 1 day | 2023-11-01 09:00 | 2023-11-01 17:00 | 100% | Post-Offer Acceptance | HR | Important
2 | Send welcome email | 1 day | 2023-11-02 09:00 | 2023-11-02 17:00 | 100% | Post-Offer Acceptance | HR | Important
3 | Register for onboarding | 1 day | 2023-11-02 09:00 | 2023-11-02 17:00 | 100% | Post-Offer Acceptance | HR | Medium
4 | Send onboarding itinerary | 1 day | 2023-11-03 09:00 | 2023-11-03 17:00 | 50% | Post-Offer Acceptance | HR | Medium
5 | Set up employee company accounts | 3 days | 2023-11-02 09:00 | 2023-11-04 17:00 | 30% | Technology | IT | Medium
6 | Set up employee badge | 1 day | 2023-11-07 09:00 | 2023-11-07 17:00 | 10% | Technology | IT | Medium
7 | Set up employee company profile | 1 day | 2023-11-07 09:00 | 2023-11-07 17:00 | 50% | Technology | IT | Medium
8 | Set up employee assets | 5 days | 2023-11-07 09:00 | 2023-11-11 17:00 | 50% | Technology | IT | Medium
9 | Send direct deposit forms | 1 day | 2023-11-07 09:00 | 2023-11-07 17:00 | 100% | Paperwork | HR | Medium
10 | Send benefits selection | 1 day | 2023-11-07 09:00 | 2023-11-07 17:00 | 100% | Paperwork | HR | Medium
11 | Send employee handbook | 1 day | 2023-11-07 09:00 | 2023-11-07 17:00 | 100% | Paperwork | HR | Medium
12 | Send Employment Eligibility Verification forms | 1 day | 2023-11-07 09:00 | 2023-11-07 17:00 | 100% | Paperwork | HR | Medium
13 | Send Relevant Tax forms | 1 day | 2023-11-07 09:00 | 2023-11-07 17:00 | 100% | Paperwork | HR | Medium
14 | Send background check forms | 1 day | 2023-11-02 09:00 | 2023-11-02 17:00 | 100% | Paperwork | HR | Medium
15 | Schedule office tour | 1 day | 2023-11-07 09:00 | 2023-11-07 17:00 | 25% | Orientation | HR | Medium
16 | Share training and orientation schedule | 1 day | 2023-11-07 09:00 | 2023-11-07 17:00 | 0% | Orientation | HR | Medium
17 | Assign a mentor | 1 day | 2023-11-07 09:00 | 2023-11-07 17:00 | 100% | Orientation | Manager | Medium
18 | Schedule meetings with members of the team | 1 day | 2023-11-07 09:00 | 2023-11-07 17:00 | 0% | Orientation | Manager | Medium
19 | Give IT assets | 1 day | 2023-11-14 09:00 | 2023-11-14 17:00 | 50% | Orientation | IT | Medium
20 | Host training and orientation sessions | 3 days | 2023-11-15 09:00 | 2023-11-17 17:00 | 0% | Orientation | HR | Medium
21 | Ask employee for onboarding feedback | 1 day | 2023-11-18 09:00 | 2023-11-18 17:00 | 0% | Feedback | HR | Medium